## SUMMARY
FLEET TELEMATICS PLATFORM - 24 MONTH ROADMAP
KEY MILESTONES
Month 5 | Phase 1 Complete | First customer lives on platform
Month 8 | Phase 1.5 Complete | BPW integration + warehouse management
Month 12 | 50 Customers | Scale to enterprise tier
Month 18 | Multi-tenancy Launch | Support unlimited customers
Month 24 | €105k MRR | €1.26M ARR achieved
FINANCIAL SUMMARY
Initial Investment | €20-30k (development) + €30k (hosting)
Break-even Month | Month 6-7 | After first customers acquired
Month 12 Revenue | €16,500/month | €198k ARR
Month 24 Revenue | €105,000/month | €1.26M ARR
Month 24 Profit | €60,000/month | After all costs
24-Month Total | €2,625,450 | Cumulative revenue
HOW TO USE THIS SPREADSHEET
1. Review each sheet for detailed plans
2. Update FINANCIALS monthly with actual data
3. Update CUSTOMER_PIPELINE as you acquire customers
4. Check RISKS and update status
5. Track KPIs against targets
6. Share SUMMARY with stakeholders monthly

## TIMELINE
Phase | Component | Start Month | End Month | Duration (weeks) | Owner | Status | Notes
Phase 1 | Backend Development | Month 1 | Month 3 | 12 | Claude | In Progress | APIs + Auth + Telematics
Phase 1 | Frontend Development | Month 1 | Month 3 | 12 | Claude | In Progress | React dashboards
Phase 1 | Database Setup | Month 1 | Month 3 | 12 | Claude | In Progress | PostgreSQL schema
Phase 1 | DevOps & Deployment | Month 2 | Month 3 | 8 | Claude | In Progress | Docker + AWS/GCP
Phase 1 | Security Hardening | Month 3 | Month 4 | 4 | Claude | In Progress | Encryption + 2FA
Phase 1 | Testing | Month 3 | Month 4 | 4 | Claude | In Progress | Unit + Integration tests
Phase 1 | Documentation | Month 2 | Month 4 | 8 | Claude | In Progress | API docs + guides
Phase 1 | First Customer Launch | Month 5 | Month 5 | 4 | You | Planning | Go live with real customer
Phase 1.5 | BPW API Integration | Month 5 | Month 6 | 6 | Claude | Planned | Search + Order + Track
Phase 1.5 | Warehouse Management | Month 6 | Month 7 | 6 | Claude | Planned | Inventory system
Phase 1.5 | Stock Alerts | Month 6 | Month 7 | 4 | Claude | Planned | Low stock notifications
Phase 1.5 | Parts Ordering | Month 7 | Month 7 | 4 | Claude | Planned | Order flow + tracking
Phase 2 | Multi-tenancy | Month 8 | Month 9 | 8 | Claude | Planned | Row-level security
Phase 2 | Advanced Compliance | Month 8 | Month 10 | 8 | Claude | Planned | Custom workflows
Phase 2 | Marketing & Sales | Month 8 | Month 12 | 16 | You | Planned | Sales push for customers
Phase 3 | Predictive ML Models | Month 10 | Month 12 | 12 | Claude | Planned | Brake prediction + AI
Phase 3 | Advanced Analytics | Month 10 | Month 12 | 12 | Claude | Planned | Cross-customer insights
Phase 4 | Mobile App Development | Month 13 | Month 15 | 12 | Claude | Planned | iOS + Android
Phase 4 | API Marketplace | Month 15 | Month 18 | 12 | Claude | Planned | Open APIs
Phase 4 | White-label Support | Month 15 | Month 18 | 12 | Claude | Planned | Reseller program

## FINANCIALS
Month | Customers | Subscription Revenue | Parts Commission | Total MRR | Hosting Costs | Team Costs | Other Costs | Total Costs | Gross Profit | Margin % | Cumulative Revenue | Cumulative Profit
Month 1 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 1000 | -1000 | -1
Month 2 | 0 | 0 | 0 | 0 | 600 | 0 | 500 | 1100 | -1100 | -1
Month 3 | 1 | 500 | 50 | 550 | 700 | 0 | 600 | 1300 | -750 | -0.73
Month 4 | 2 | 1000 | 150 | 1150 | 800 | 2000 | 700 | 3500 | -2350 | -0.67
Month 5 | 3 | 1500 | 300 | 1800 | 900 | 2000 | 800 | 3700 | -1900 | -0.51
Month 6 | 5 | 2500 | 500 | 3000 | 1000 | 2500 | 900 | 4400 | -1400 | -0.32
Month 7 | 8 | 4000 | 1200 | 5200 | 1200 | 3000 | 1000 | 5200 | 0 | 0
Month 8 | 12 | 6000 | 2000 | 8000 | 1500 | 3000 | 1200 | 5700 | 2300 | 0.29
Month 9 | 15 | 7500 | 3000 | 10500 | 1800 | 3500 | 1400 | 6700 | 3800 | 0.36
Month 10 | 20 | 10000 | 4500 | 14500 | 2000 | 4000 | 1600 | 7600 | 6900 | 0.48
Month 11 | 25 | 12500 | 5000 | 17500 | 2200 | 4500 | 1800 | 8500 | 9000 | 0.51
Month 12 | 25 | 12500 | 4000 | 16500 | 2500 | 5000 | 2000 | 9500 | 7000 | 0.42
Month 18 | 50 | 25000 | 12000 | 37000 | 4000 | 8500 | 3200 | 15700 | 21300 | 0.58
Month 24 | 100 | 50000 | 35000 | 85000 | 6500 | 13000 | 5500 | 25000 | 60000 | 0.71

## FEATURES
Phase | Feature | Component | Priority | Start Month | End Month | Status | Owner | Effort (days) | Notes
Phase 1 | Authentication | Backend | P0 | Month 1 | Month 2 | In Progress | Claude | 5 | JWT + 2FA
Phase 1 | Real-time Telematics | Backend | P0 | Month 1 | Month 3 | In Progress | Claude | 15 | 3 providers
Phase 1 | Vehicle Management | Backend | P0 | Month 1 | Month 2 | In Progress | Claude | 5 | CRUD APIs
Phase 1 | Driver Management | Backend | P0 | Month 1 | Month 2 | In Progress | Claude | 5 | License tracking
Phase 1 | Tachograph Monitoring | Backend | P0 | Month 2 | Month 3 | In Progress | Claude | 10 | Infringements
Phase 1 | CPC Training | Backend | P0 | Month 2 | Month 3 | In Progress | Claude | 8 | Course booking
Phase 1 | Alert System | Backend | P0 | Month 2 | Month 3 | In Progress | Claude | 8 | Notifications
Phase 1 | Dashboard UI | Frontend | P0 | Month 1 | Month 3 | In Progress | Claude | 20 | React
Phase 1 | Real-time Map | Frontend | P0 | Month 2 | Month 3 | In Progress | Claude | 8 | Mapbox
Phase 1.5 | BPW API Integration | Backend | P0 | Month 5 | Month 6 | Planned | Claude | 5 | Search/Order
Phase 1.5 | Warehouse Inventory | Backend | P0 | Month 6 | Month 7 | Planned | Claude | 10 | Stock mgmt
Phase 1.5 | Stock Alerts | Backend | P0 | Month 6 | Month 7 | Planned | Claude | 5 | Low stock
Phase 2 | Multi-tenancy RLS | Backend | P0 | Month 8 | Month 9 | Planned | Claude | 10 | Security
Phase 3 | Brake Pad Prediction | Backend | P0 | Month 10 | Month 12 | Planned | Claude | 20 | ML Model
Phase 4 | Mobile App | Frontend | P2 | Month 13 | Month 15 | Planned | Claude | 30 | iOS/Android

## CUSTOMER_PIPELINE
Month | Starting | New | Churn | Ending | Churn Rate % | Avg Spend € | Notes
Month 6 | 6 | 4 | 0 | 10 | 0 | 800 | Growing
Month 12 | 25 | 12 | 1 | 36 | 2.1 | 1100 | Strong growth
Month 18 | 50 | 10 | 1 | 59 | 1.7 | 1300 | Scaling
Month 24 | 100 | 0 | 3 | 97 | 1.6 | 1530 | Enterprise focus

## INFRASTRUCTURE
Month | Compute | Database | Storage | CDN | ML/Analytics | Monitoring | Backups | Misc | Total Monthly | Cumulative
Month 3 | 400 | 150 | 50 | 15 | 0 | 35 | 30 | 25 | 705 | 1805
Month 6 | 550 | 300 | 80 | 30 | 100 | 60 | 50 | 40 | 1210 | 4820
Month 12 | 1100 | 600 | 180 | 80 | 400 | 120 | 120 | 90 | 2690 | 17030
Month 18 | 2300 | 1200 | 340 | 180 | 1100 | 220 | 240 | 220 | 5800 | 43950
Month 24 | 3600 | 1800 | 520 | 300 | 1700 | 340 | 360 | 360 | 9080 | 90270

## KPIs
Metric | Category | Target | Definition | Month 6 | Month 12 | Month 18 | Month 24
MRR | Business | €100k | Monthly recurring revenue | €3,000 | €16,500 | €49,500 | €105,000
Customer Count | Business | 100 | Total paying customers | 10 | 25 | 50 | 100
Churn Rate | Business | <3% | Monthly churn | 0% | 2.1% | 2.0% | 1.6%
CAC | Business | <€2,000 | Customer acquisition cost | €1,500 | €1,800 | €2,000 | €1,900
Uptime | Operations | >99.9% | System availability | N/A | 99.95% | 99.97% | 99.98%
Response Time | Operations | <200ms | Avg API response | N/A | 150ms | 120ms | 100ms
Feature Adoption | Product | >80% | % using new features | N/A | 85% | 90% | 92%
Alert Accuracy | Product | >95% | Correct predictions | N/A | 93% | 96% | 97%
Gross Margin | Finance | >85% | Revenue - COGS | N/A | 45% | 60% | 70%
Burn Rate | Finance | <€5k | Monthly cash spend | €2,000 | €4,000 | €5,000 | €6,000

## RISKS
Risk | Category | Likelihood | Impact | Mitigation | Owner | Status
API provider changes API | Technical | Medium | High | Build adapter pattern, abstract integrations | Claude | Monitored
Database performance | Technical | Low | High | Load testing, caching, optimization | Claude | Mitigated
Customers don't value AI | Business | Medium | High | Focus on compliance first, AI later | You | Monitored
Competitors copy idea | Business | Medium | Medium | Build network effects, patents, brand | You | Mitigated
Can't find first customers | Business | High | High | Pre-sell before building, use network | You | Active
Hosting costs exceed plan | Financial | Low | Medium | Right-size, use reserved instances | You | Mitigated
Key supplier changes pricing | Market | Low | Medium | Negotiate contracts, backup suppliers | You | Mitigated
GDPR compliance issues | Regulatory | Low | High | Consult expert, implement deletion/audit | Claude | Mitigated
Key person dependency | Operational | High | High | Document everything, hire strong team | You | Active